## Slide 2: Software Project Planning
After the finalization of SRS, we would estimate size, cost and development time
like to of the
project. Also, in many cases, customer may like to know the cost and development time even prior to finalization of the SRS.

## Slide 3: Software Project Planning
In order to conduct a successful software project, we must understand:
Scope of work to be done
The risk to be incurred
The resources required
The task to be accomplished
The cost to be expended
The schedule to be followed

## Slide 4: Software Project Planning
Software planning begins before technical work starts, continues as the software evolves from concept to reality, and culminates only when the software is retired.
Size estimation
Cost estimation
Development time
Resources requirements
Project scheduling
Fig. 1: Activities during Software Project Planning

## Slide 5: Software Project Planning
1. | int. sort (int x[ ], int n)
2. | {
3. | int i, j, save, im1;
4. | /*This function sorts array x in ascending order */
5. | If (n<2) return 1;
6. | for (i=2; i<=n; i++)
7. | {
8. | im1=i-1;
9. | for (j=1; j<=im; j++)
10. | if (x[i] < x[j])
11. | {
12. | Save = x[i];
13. | x[i] = x[j];
14. | x[j] = save;
15. | }
16. | }
17. | return 0;
18. | }
Size Estimation
Lines of Code (LOC)
If LOC is simply a count of the number of lines then figure shown below contains 18 LOC .
When comments and blank lines are ignored, the program in figure 2 shown below contains 17 LOC.
Fig. 2: Function for sorting an array

## Slide 6: Software Project Planning
0
500,000
1,000,000
1,500,000
2,000,000
2,500,000
Jan 1993
Jun 1994
Oct 1995
Mar 1997
Jul 1998
Dec 1999
Apr 2001
Total LOC
Total LOC ("wc -l") -- development releases Total LOC ("wc -l") -- stable releases
Total LOC uncommented -- development releases Total LOC uncommented -- stable releases
Growth of Lines of Code (LOC)

## Slide 7: Software Project Planning
Furthermore, if the main interest is the size of the program for specific functionality, it may be reasonable to include executable statements. The only executable statements in figure shown above are in lines 5-17 leading to a count of
13. The differences in the counts are 18 to 17 to 13. One can easily see the potential for major discrepancies for
large programs with many comments or programs written in language that allow a large number of descriptive but non-executable statement. Content has defined lines of code as:

## Slide 8: Software Project Planning
“A line of code is any line of program text that is not a comment or blank line, regardless of the number of statements or fragments of statements on the line. This specifically includes all lines containing program header, declaration, and executable and non-executable statements”.
This is the predominant definition for lines of code used by researchers. By this definition, figure shown above has 17 LOC.

## Slide 9: Software Project Planning
Function Count
Alan Albrecht while working for IBM, recognized the problem in size measurement in the 1970s, and developed a technique (which he called Function Point Analysis), which appeared to be a solution to the size measurement problem.

## Slide 10: Software Project Planning
The principle of Albrecht’s function point analysis (FPA) is that a system is decomposed into functional units.
Inputs
Outputs
Enquiries
:
:
:
Internal logical files
:
External interface files
:
information entering the system information leaving the system
requests for instant access to information
information held within the system
information held by other system that is used by the system being analyzed.

## Slide 11: Software Project Planning
ILF
EIF
User
applications
System
Outputs
Inputs
The FPA functional units are shown in figure given below:
User
Inquiries
Other
ILF: Internal logical files EIF: External interfaces
Fig. 3: FPAs functional units System

## Slide 12: Software Project Planning
The five functional units are divided in two categories:
(i) Data function types
Internal Logical Files (ILF): A user identifiable group of logical related data or control information maintained within the system.
External Interface files (EIF): A user identifiable group of logically related data or control information referenced by the system, but maintained within another system. This means that EIF counted for one system, may be an ILF in another system.

## Slide 13: Software Project Planning
Transactional function types
  External Input (EI): An EI processes data or control information that comes from outside the system. The EI is an elementary process, which is the smallest unit of activity that is meaningful to the end user in the business.
  External Output (EO): An EO is an elementary process that generate data or control information to be sent outside the system.
  External Inquiry (EQ): An EQ is an elementary process that is made up to an input-output combination that results in data retrieval.

## Slide 14: Software Project Planning
Special features
Function point approach is independent of the language, tools, or methodologies used for implementation; i.e. they do not take into consideration programming languages, data base management systems, processing hardware or any other data base technology.
Function points can be estimated from requirement specification or design specification, thus making it possible to estimate development efforts in early phases of development.

## Slide 15: Software Project Planning
Function points are directly linked to the statement of requirements; any change of requirements can easily be followed by a re-estimate.
Function points are based on the system user’s external view of the system, non-technical users of the software system have a better understanding of what function points are measuring.

## Slide 16: Software Project Planning
Counting function points
Functional Units | Weighting factors |  | 
 | Low | Average | High
External Inputs (EI) | 3 | 4 | 6
External Output (EO) | 4 | 5 | 7
External Inquiries (EQ) | 3 | 4 | 6
External logical files (ILF) | 7 | 10 | 15
External Interface files (EIF) | 5 | 7 | 10
Table 1 : Functional units with weighting factors

## Slide 17: Software Project Planning
Table 2: UFP calculation table
Functional Units |  | Count Complexity |  |  | Complexity Totals |  |  | Functional Unit Totals |  | 
External Inputs (EIs) |  | Low x 3 Average x 4 |  | = = |  |  |  |  |  | 
 |  |  | High x 6 | = |  |  |  |  |  | 
External Outputs (EOs) |  | Low x 4 Average x 5 |  | = = |  |  |  |  |  | 
 |  |  | High x 7 | = |  |  |  |  |  | 
External Inquiries (EQs) |  | Low x 3 Average x 4 |  | = = |  |  |  |  |  | 
 |  |  | High x 6 | = |  |  |  |  |  | 
External logical Files (ILFs) |  | Low x 7 Average x 10 High x 15 |  | = = = |  |  |  |  |  | 
External Interface Files (EIFs) |  | Low x 5 Average x 7 |  | = = |  |  |  |  |  | 
 |  |  | High x 10 | = |  |  |  |  |  | 
Total Unadjusted Function Point Count |  |  |  |  |  |  |  |  |  | 

## Slide 18: Software Project Planning
The weighting factors are identified for all functional units and multiplied with the functional units accordingly. The procedure for the calculation of Unadjusted Function Point (UFP) is given in table shown above.

## Slide 19: Software Project Planning
The procedure for the calculation of UFP in mathematical form is given below:
5 3
UFP  ∑∑ Zij wij
i1 J 1
Where i indicate the row and j indicates the column of Table 1
Wij : It is the entry of the ith row and jth column of the table 1
Zij : It is the count of the number of functional units of Type i that have been classified as having the complexity corresponding to column j.

## Slide 20: Software Project Planning
Organizations that use function point methods develop a criterion for determining whether a particular entry is Low, Average or High. Nonetheless, the determination of complexity is somewhat subjective.
FP = UFP * CAF
Where CAF is complexity adjustment factor and is equal to [0.65 +
0.01 x ΣFi]. The Fi (i=1 to 14) are the degree of influence and are based on responses to questions noted in table 3.

## Slide 21: Software Project Planning
5
4
Table 3 : Computing function points.
Rate each factor on a scale of 0 to 5.
0 1 2 3
No Influence
Average
Essential
Incidental Moderate Significant
Number of factors considered ( Fi )
Does the system require reliable backup and recovery ?
Is data communication required ?
Are there distributed processing functions ?
Is performance critical ?
Will the system run in an existing heavily utilized operational environment ?
Does the system require on line data entry ?
Does the on line data entry require the input transaction to be built over multiple screens or operations ?
Are the master files updated on line ?
Is the inputs, outputs, files, or inquiries complex ?
Is the internal processing complex ?
Is the code designed to be reusable ?
Are conversion and installation included in the design ?
Is the system designed for multiple installations in different organizations ?
Is the application designed to facilitate change and ease of use by the user ?

## Slide 22: Software Project Planning
Functions points may compute the following important metrics:
Productivity Quality | = = | FP / persons-months Defects / FP
Cost | = | Rupees / FP
Documentation | = | Pages of documentation per FP
These metrics are controversial and are not universally acceptable. There are standards issued by the International Functions Point User Group (IFPUG, covering the Albrecht method) and the United Kingdom Function Point User Group (UFPGU, covering the MK11 method). An ISO standard for function point method is also being developed.

## Slide 23: Software Project Planning
Example: 4.1
Consider a project with the following functional units:
Number of user inputs Number of user outputs Number of user enquiries Number of user files
Number of external interfaces
= 50
= 40
= 35
= 06
= 04
Assume all complexity adjustment factors and weighting factors are average. Compute the function points for the project.

## Slide 24: Software Project Planning
Solution
We know
5 3
UFP  ∑∑ Zij wij
i1 J 1
UFP = 50 x 4 + 40 x 5 + 35 x 4 + 6 x 10 + 4 x 7
= 200 + 200 + 140 + 60 + 28 = 628
CAF = (0.65 + 0.01 ΣFi)
= (0.65 + 0.01 (14 x 3)) = 0.65 + 0.42 = 1.07 FP = UFP x CAF
= 628 x 1.07 = 672

## Slide 25: Software Project Planning
Example:4.2
An application has the following:
10 low external inputs, 12 high external outputs, 20 low
internal logical files, 15 high external interface files, 12 average external inquiries, and a value of complexity
adjustment factor of 1.10.
What are the unadjusted and adjusted function point counts ?

## Slide 26: Software Project Planning
FP
= UFP x CAF
= 452 x 1.10 = 497.2.
Solution
Unadjusted function point counts may be calculated using as:
5 3
UFP  ∑∑ Zij wij
i1 J 1
= 10 x 3 + 12 x 7 + 20 x 7 + 15 + 10 + 12 x 4
= 30 + 84 +140 + 150 + 48
= 452

## Slide 27: Software Project Planning
Example: 4.3
Consider a project with the following parameters.
External Inputs:
  10 with low complexity (b)15 with average complexity
(c) 17 with high complexity
External Outputs:
  6 with low complexity (b)13 with high complexity
External Inquiries:
  3 with low complexity
  4 with average complexity
  2 high complexity

## Slide 28: Software Project Planning
Internal logical files:
  2 with average complexity (b)1 with high complexity
External Interface files:
  9 with low complexity
In addition to above, system requires
Significant data communication
Performance is very critical
Designed code may be moderately reusable
System is not designed for multiple installation in different organizations.
Other complexity adjustment factors are treated as average. Compute the function points for the project.
CAF= 1.06

## Slide 29: Software Project Planning
Solution: Unadjusted function points may be counted using table 2
Functional Units | Count | Complexity |  | Complexity Totals |  |  | Functional Unit Totals
External Inputs | 10 15 | Low x 3 Average x 4 | = = |  | 30 60 |  | 
(EIs) | 17 | High x 6 | = |  | 102 | 192 | 
External Outputs (EOs) | 6 0 13 | Low x 4 Average x 5 High x 7 | = = = |  | 24 0 91 | 115 | 
External Inquiries (EQs) | 3 4 2 | Low x 3 Average x 4 High x 6 | = = = |  | 9 16 12 | 37 | 
External logical | 0 2 | Low x 7 Average x 10 | = = |  | 0 20 |  | 
Files (ILFs) | 1 | High x 15 | = |  | 15 | 35 | 
External | 9 | Low x 5 Average x 7 High x 10 | = = = |  | 45 |  | 
Interface | 0 |  |  |  | 0 |  | 
Files (EIFs) | 0 |  |  |  | 0 | 45 | 
 | Total Unadjusted Function Point Count |  |  |  |  |  | 424

## Slide 30: Software Project Planning
FP = UFP x CAF
= 424 x 1.06
= 449.44
Hence FP = 449

## Slide 31
Relative Cost of Software Phases
Software Project Planning

## Slide 32: Software Project Planning
Cost Estimation
A number of estimation techniques have been developed and are having following attributes in common :
Project scope must be established in advance
Software metrics are used as a basis from which estimates are made
The project is broken into small pieces which are estimated individually
To achieve reliable cost and schedule estimates, a number of options arise:
Delay estimation until late in project
Use simple decomposition techniques to generate project cost and schedule estimates
Develop empirical models for estimation
Acquire one or more automated estimation tools

## Slide 33: Software Project Planning
MODELS
Static, Single Variable Models
Static, Multivariable Models

## Slide 34: Software Project Planning
C = a Lb
Static, Single Variable Models
Methods using this model use an equation to estimate the desired values such as cost, time, effort, etc. They all depend on the same variable used as predictor (say, size). An example of the most common equations is :
(i)
C is the cost, L is the size and a,b are constants
E = 1.4 L0.93 DOC = 30.4 L0.90 D = 4.6 L0.26
Effort (E in Person-months), documentation (DOC, in number of pages) and duration (D, in months) are calculated from the number of lines of code (L, in thousands of lines) used as a predictor.

## Slide 35: Software Project Planning
E D
= 5.2 L0.91
= 4.1 L0.36
Static, Multivariable Models
These models are often based on equation (i), they actually depend on several variables representing various aspects of the software development environment, for example method used, user participation, customer oriented changes, memory constraints, etc.
29
The productivity index uses 29 variables which are found to be highly correlated to productivity as follows:
  ∑Wi Xi
i1

## Slide 36: Software Project Planning
Example: 4.4
Compare the Walston-Felix model with the SEL model on a software development expected to involve 8 person-years of effort.
code that can be
Calculate the number of lines of source produced.
Calculate the duration of the development. (c)Calculate the productivity in LOC/PY

## Slide 37: Software Project Planning
Solution
The amount of manpower involved = 8 PY = 96 person-months
(a) Number of lines of source code can be obtained by reversing equation to give:
L = (E/a)1/b
Then
L(SEL) = (96/1.4)1/0.93 = 94264 LOC L(SEL) = (96/5.2)1/0.91 = 24632 LOC.

## Slide 38: Software Project Planning
Duration in months can be calculated by means of equation D(SEL) = 4.6 (L)0.26
= 4.6 (94.264)0.26 = 15 months D(W-F) = 4.1 L0.36
= 4.1(24.632)0.36 = 13 months
Productivity is the lines of code produced per person/month (year)
P(SEL)  94264  11783 LOC / Person  Years
8
8
P(W  F )  24632  3079 LOC / Person  Years

## Slide 39: Software Project Planning
Basic Intermediate Detailed
Model proposed by
B. W. Boehm’s through his book
Software Engineering Economics in 1981
The Constructive Cost Model (COCOMO)
Constructive Cost model (COCOMO)

## Slide 40: Software Project Planning
COCOMO applied to
Semidetached mode
Embedded mode
Organic mode

## Slide 41: Software Project Planning
Mode | Project size | Nature of Project | Innovation | Deadline of the project | Development Environment
Organic | Typically 2-50 KLOC | Small size project, experienced developers in the familiar environment. For example, pay roll, inventory projects etc. | Little | Not tight | Familiar & In house
Semi detached | Typically 50-300 KLOC | Medium size project, Medium size team, Average previous experience on similar project. For example: Utility systems like compilers, database systems, editors etc. | Medium | Medium | Medium
Embedded | Typically over 300 KLOC | Large project, Real time systems, Complex interfaces, Very little previous experience. For example: ATMs, Air Traffic Control etc. | Significant | Tight | Complex Hardware/ customer Interfaces required
Table 4: The comparison of three COCOMO modes

## Slide 42: Boehm’s definition of organic, semidetached, and embedded systems:
Organic – A software project is said to be an organic type if the team size required is adequately small, the problem is well understood and has been solved in the past and also the team members have a nominal experience regarding the problem.
Semi-detached – A software project is said to be a Semi-detached type if the vital characteristics such as team-size, experience, knowledge of the various programming environment lie in between that of organic and Embedded. The projects classified as Semi-Detached are comparatively less familiar and difficult to develop compared to the organic ones and require more experience and better guidance and creativity. Eg: Compilers or different Embedded Systems can be considered of Semi-Detached type.
Embedded – A software project with requiring the highest level of complexity, creativity, and experience requirement fall under this category. Such software requires a larger team size than the other two models and also the developers need to be sufficiently experienced and creative to develop such complex models.

## Slide 43: Software Project Planning
Basic Model
Basic COCOMO model takes the form
E  a (KLOC)bb
b
b
d
b
D  c (E)
where E is effort applied in Person-Months, and D is the development time in months. The coefficients ab, bb, cb and db are given in table 4 (a).

## Slide 44: Software Project Planning
Software Project | ab | bb | cb | db
Organic | 2.4 | 1.05 | 2.5 | 0.38
Semidetached | 3.0 | 1.12 | 2.5 | 0.35
Embedded | 3.6 | 1.20 | 2.5 | 0.32
Table 4(a): Basic COCOMO coefficients

## Slide 45: Software Project Planning
When effort and development time are known, the average staff size to complete the project may be calculated as:
Persons
D
E
Average staff size (SS ) 
When project size is known, the productivity
level may be
E
calculated as:
Productivity (P)  KLOC KLOC / PM

## Slide 46: Software Project Planning
Example: 4.5
Suppose that a project was estimated to be 400 KLOC. Calculate the effort and development time for each of the three modes i.e., organic, semidetached and embedded.

## Slide 47: Software Project Planning
Solution
The basic COCOMO equation take the form:
bb
E  ab (KLOC)
b
D  c (KLOC)db
Estimated size of the project = 400 KLOC
(i) Organic mode
E = 2.4(400)1.05 = 1295.31 PM
D = 2.5(1295.31)0.38 = 38.07 PM

## Slide 48: Software Project Planning
Semidetached mode
E = 3.0(400)1.12 = 2462.79 PM
D = 2.5(2462.79)0.35 = 38.45 PM
Embedded mode
E = 3.6(400)1.20 = 4772.81 PM
D = 2.5(4772.8)0.32 = 38 PM

## Slide 49: Software Project Planning
Example: 4.6
A project size
of 200 KLOC is to be developed. Software
development team has average experience on similar type of projects. The project schedule is not very tight. Calculate the effort, development time, average staff size and productivity of the project.

## Slide 50: Software Project Planning
Solution
The semi-detached mode is the most appropriate mode; keeping in view the size, schedule and experience of the development team.
E = 3.0(200)1.12 = 1133.12 PM
D = 2.5(1133.12)0.35 = 29.3 PM
Hence
Persons
D
E
Average staff size (SS ) 
29.3
 1133.12  38.67Persons

## Slide 51: Software Project Planning
Productivity
KLOC
E 1133.12
200
 0.1765 KLOC / PM


P  176 LOC / PM

## Slide 52: Software Project Planning
Intermediate Model
Cost drivers
(ii)
Product Attributes
  Required s/w reliability
  Size of application database
  Complexity of the product Hardware Attributes
  Run time performance constraints
  Memory constraints
  Virtual machine volatility
  Turnaround time

## Slide 53: Software Project Planning
Personal Attributes
  Analyst capability
  Programmer capability
  Application experience
  Virtual m/c experience
  Programming language experience
Project Attributes
  Modern programming practices
  Use of software tools
  Required development Schedule

## Slide 54: Software Project Planning
Cost Drivers | RATINGS |  |  |  |  | 
 | Very low | Low | Nominal | High | Very high | Extra high
Product Attributes |  |  |  |  |  | 
RELY | 0.75 | 0.88 | 1.00 | 1.15 | 1.40 | --
DATA | -- | 0.94 | 1.00 | 1.08 | 1.16 | --
CPLX | 0.70 | 0.85 | 1.00 | 1.15 | 1.30 | 1.65
Computer Attributes |  |  |  |  |  | 
TIME | -- | -- | 1.00 | 1.11 | 1.30 | 1.66
STOR | -- | -- | 1.00 | 1.06 | 1.21 | 1.56
VIRT | -- | 0.87 | 1.00 | 1.15 | 1.30 | --
TURN | -- | 0.87 | 1.00 | 1.07 | 1.15 | --
Multipliers of different cost drivers

## Slide 55: Software Project Planning
Cost Drivers | RATINGS |  |  |  |  | 
 | Very low | Low | Nominal | High | Very high | Extra high
Personnel Attributes |  |  |  |  |  | 
ACAP | 1.46 | 1.19 | 1.00 | 0.86 | 0.71 | --
AEXP | 1.29 | 1.13 | 1.00 | 0.91 | 0.82 | --
PCAP | 1.42 | 1.17 | 1.00 | 0.86 | 0.70 | --
VEXP | 1.21 | 1.10 | 1.00 | 0.90 | -- | --
LEXP | 1.14 | 1.07 | 1.00 | 0.95 | -- | --
Project Attributes |  |  |  |  |  | 
MODP | 1.24 | 1.10 | 1.00 | 0.91 | 0.82 | --
TOOL | 1.24 | 1.10 | 1.00 | 0.91 | 0.83 | --
SCED | 1.23 | 1.08 | 1.00 | 1.04 | 1.10 | --
Table 5: Multiplier values for effort calculations

## Slide 56: Software Project Planning
Project | ai | bi | ci | di
Organic | 3.2 | 1.05 | 2.5 | 0.38
Semidetached | 3.0 | 1.12 | 2.5 | 0.35
Embedded | 2.8 | 1.20 | 2.5 | 0.32
Table 6: Coefficients for intermediate COCOMO
Intermediate COCOMO equations
E  a (KLOC)bi * EAF
i
i
D  c (E)di

## Slide 57: Software Project Planning
Phase-Sensitive effort multipliers
Three level product hierarchy
Modules subsystem
System level
Cost drivers
design & test
Manpower allocation for each phase
Detailed COCOMO Model
Detailed COCOMO

## Slide 58: Software Project Planning
Development Phase
: 6% to 8%
: 10% to 40%
Plan / Requirements
EFFORT DEVELOPMENT TIME
% depend on mode & size

## Slide 59: Software Project Planning
Design
Effort Time
:
:
16% to 18%
19% to 38%
Programming
Effort Time
:
:
48% to 68%
24% to 64%
Integration & Test
Effort Time
:
:
16% to 34%
18% to 34%

## Slide 60: Software Project Planning
Principle of the effort estimate
Size equivalent
As the software might be partly developed from software already existing (that is, re-usable code), a full development is not always required. In such cases, the parts of design document (DD%), code (C%) and integration (I%) to be modified are estimated. Then, an adjustment factor, A, is calculated by means of the following equation.
A = 0.4 DD + 0.3 C + 0.3 I
The size equivalent is obtained by
S (equivalent) = (S x A) / 100
Ep   p E
Dp   p D

## Slide 61: Software Project Planning Lifecycle Phase Values of  p
Mode & Code Size | Plan & Requirements | System Design | Detailed Design | Module Code & Test | Integration & Test
Organic Small S≈2 | 0.06 | 0.16 | 0.26 | 0.42 | 0.16
Organic medium S≈32 | 0.06 | 0.16 | 0.24 | 0.38 | 0.22
Semidetached medium S≈32 | 0.07 | 0.17 | 0.25 | 0.33 | 0.25
Semidetached large S≈128 | 0.07 | 0.17 | 0.24 | 0.31 | 0.28
Embedded large S≈128 | 0.08 | 0.18 | 0.25 | 0.26 | 0.31
Embedded extra large S≈320 | 0.08 | 0.18 | 0.24 | 0.24 | 0.34
Table 7 : Effort and schedule fractions occurring in each phase of the lifecycle

## Slide 62: Software Project Planning Lifecycle Phase Values of  p
Mode & Code Size | Plan & Requirements | System Design | Detailed Design | Module Code & Test | Integration & Test
Organic Small S≈2 | 0.10 | 0.19 | 0.24 | 0.39 | 0.18
Organic medium S≈32 | 0.12 | 0.19 | 0.21 | 0.34 | 0.26
Semidetached medium S≈32 | 0.20 | 0.26 | 0.21 | 0.27 | 0.26
Semidetached large S≈128 | 0.22 | 0.27 | 0.19 | 0.25 | 0.29
Embedded large S≈128 | 0.36 | 0.36 | 0.18 | 0.18 | 0.28
Embedded extra large S≈320 | 0.40 | 0.38 | 0.16 | 0.16 | 0.30
Table 7 : Effort and schedule fractions occurring in each phase of the lifecycle

## Slide 63: Software Project Planning
Distribution of software life cycle:
Requirement and product design
  Plans and requirements (b)System design
Detailed Design
  Detailed design
Code & Unit test
  Module code & test
Integrate and Test
  Integrate & Test

## Slide 64: Software Project Planning
Example: 4.7
A new project with estimated 400 KLOC embedded system has to be developed. Project manager has a choice of hiring from two pools of
developers: Very highly capable with very little experience in the
programming language being used Or
Developers of low quality but a lot of experience with the programming language. What is the impact of hiring all developers from one or the other pool ?

## Slide 65: Software Project Planning
Solution
case of embedded mode and model is intermediate
= 2.8 (400)1.20 = 3712 PM
Case I: Developers are very highly capable with very little experience in the programming being used.
EAF = 0.82 x 1.14 = 0.9348
E = 3712 x .9348 = 3470 PM
D = 2.5 (3470)0.32 = 33.9 M
This is the COCOMO.
Hence
i
E  a (KLOC)di

## Slide 66: Software Project Planning
Case II: Developers are of low quality but lot of experience with the programming language being used.
EAF = 1.29 x 0.95 = 1.22
E = 3712 x 1.22 = 4528 PM
D = 2.5 (4528)0.32 = 36.9 M
Case II requires more effort and time. Hence, low quality developers with lot of programming language experience could not match with the performance of very highly capable developers with very litter experience.

## Slide 67: Software Project Planning
Example: 4.8
Consider a project to develop a full screen editor. The major components identified are:
Screen edit
Command Language Interpreter
File Input & Output
Cursor Movement
Screen Movement
The size of these are estimated to be 4k, 2k, 1k, 2k and 3k delivered source code lines. Use COCOMO to determine
Overall cost and schedule estimates (assume values for different cost drivers, with at least three of them being different from 1.0)
Cost & Schedule estimates for different phases.

## Slide 68: Software Project Planning
Solution
Size of five modules are:
Screen edit
Command language interpreter File input and output
Cursor movement Screen movement
Total
= 4 KLOC
= 2 KLOC
= 1 KLOC
= 2 KLOC
= 3 KLOC
= 12 KLOC

## Slide 69: Software Project Planning
Let us assume that significant cost drivers are
Required software reliability is high, i.e.,1.15
Product complexity is high, i.e.,1.15
Analyst capability is high, i.e.,0.86
Programming language experience is low,i.e.,1.07
All other drivers are nominal
EAF = 1.15x1.15x0.86x1.07 = 1.2169

## Slide 70: Software Project Planning
(a) The initial effort estimate for the project is obtained from the following equation
Development time
E = ai (KLOC)bi x EAF
= 3.2(12)1.05 x 1.2169 = 52.91 PM
D = Ci(E)di
= 2.5(52.91)0.38 = 11.29 M
(b) Using the following equations and referring Table 7, phase wise cost and schedule estimates can be calculated.
Ep   p E
Dp   p D

## Slide 71: Software Project Planning
Since size is only 12 KLOC, it is an organic small model. Phase wise effort distribution is given below:
System Design Detailed Design Module Code & Test Integration & Test
= 0.16 x 52.91 = 8.465 PM
= 0.26 x 52.91 = 13.756 PM
= 0.42 x 52.91 = 22.222 PM
= 0.16 x 52.91 = 8.465 Pm
Now Phase wise development time duration is
System Design Detailed Design Module Code & Test Integration & Test
= 0.19 x 11.29 = 2.145 M
= 0.24 x 11.29 = 2.709 M
= 0.39 x 11.29 = 4.403 M
= 0.18 x 11.29 = 2.032 M

## Slide 72: Software Project Planning
COCOMO-II
The following categories of applications / projects are identified by COCOMO-II and are shown in fig. 4 shown below:
End user programming | Application generators & composition aids | Infrastructure
 | Application composition | 
 | System integration | 
Fig. 4 : Categories of applications / projects

## Slide 73: Software Project Planning
Table 8: Stages of COCOMO-II
Stage No | Model Name | Application for the types of projects | Applications
Stage I | Application composition estimation model | Application composition | In addition to application composition type of projects, this model is also used for prototyping (if any) stage of application generators, infrastructure & system integration.
Stage II | Early design estimation model | Application generators, infrastructure & system integration | Used in early design stage of a project, when less is known about the project.
Stage III | Post architecture estimation model | Application generators, infrastructure & system integration | Used after the completion of the detailed architecture of the project.

## Slide 74: Software Project Planning
75
Software Engineering (3 ed.), By K.K Aggarwal & Yogesh Singh, Copyright © New Age International Publishers, 2007
Application Composition Estimation Model
Fig.5: Steps frdor the estimation of effort in person months

## Slide 75: Software Project Planning
Assess object counts: Estimate the number of screens, reports and 3 GL components that will comprise this application.
Classification of complexity levels: We have to classify each object instance into simple, medium and difficult complexity levels depending on values of its characteristics.
Table 9 (a): For screens

## Slide 76: Software Project Planning
Table 9 (b): For reports

## Slide 77: Software Project Planning
iii. Assign complexity weight to each object : The weights are used for three object types i.e., screen, report and 3GL components using the Table 10.
Table 10: Complexity weights for each level

## Slide 78: Software Project Planning
Determine object points: Add all the weighted object instances to get one number and this known as object-point count.
Compute new object points: We have to estimate the percentage of reuse to be achieved in a project. Depending on the percentage reuse, the new object points (NOP) are computed.
(object points) * (100-%reuse)
NOP = -------------------------------------------
100
NOP are the object points that will need to be developed and differ from the object point count because there may be reuse.

## Slide 79: Software Project Planning
of productivity rate: The productivity rate can be
vi. Calculation
calculated as:
Productivity rate (PROD) = NOP/Person month
Table 11: Productivity values

## Slide 80: Software Project Planning
vii. Compute the effort in Persons-Months: When PROD is known, we may estimate effort in Person-Months as:
NOP
Effort in PM = ------------
PROD

## Slide 81: Software Project Planning
Example: 4.9
Consider a database application project with the following characteristics:
The application has 4 screens with 4 views each and 7 data tables for 3 servers and 4 clients.
The application may generate two report of 6 sections each from 07 data tables for two server and 3 clients. There is 10% reuse of object points.
The developer’s experience and capability in the similar environment is low. The maturity of organization in terms of capability is also low. Calculate the object point count, New object points and effort to develop such a project.

## Slide 82: Software Project Planning
Solution
This project comes under the category of application composition estimation model.
Number of screens = 4 with 4 views each Number of reports = 2 with 6 sections each
From Table 9 we know that each screen will be of medium complexity and each report will be difficult complexity.
Using Table 10 of complexity weights, we may calculate object point count.
= 4 x 2 + 2 x 8 = 24
24 * (100 -10)
NOP = -------------------- = 21.6
100

## Slide 83: Software Project Planning
Table 11 gives the low value of productivity (PROD) i.e. 7.
NOP
Efforts in PM = -----------
PROD
21.6
Efforts = ----------- = 3.086 PM
7

## Slide 84: Software Project Planning
The Early Design Model
The COCOMO-II models use the base equation of the form
PMnominal = A * (size)B
where
PMnominal = Effort of the project in person months
A = Constant representing the nominal productivity, provisionally set to 2.5
B = Scale factor
Size = Software size

## Slide 85: Software Project Planning
Scale factor |  | Explanation |  |  | Remarks
Precedentness |  | Reflects the previous experience on similar projects. This is applicable to individuals & organization both in terms of expertise & experience |  |  | Very low means no previous experiences, Extra high means that organization is completely familiar with this application domain.
Development flexibility |  | Reflect the degree of flexibility in the development process. |  |  | Very low means a well defined process is used. Extra high means that the client gives only general goals.
Architecture/ resolution | Risk | Reflect the degree analysis carried out. | of | risk | Very low means very little analysis and Extra high means complete and through risk analysis.
Cont…
Table 12: Scaling factors required for the calculation of the value of B

## Slide 86: Software Project Planning
Table 12: Scaling factors required for the calculation of the value of B
Scale factor | Explanation | Remarks
Team cohesion | Reflects the team management skills. | Very low means no previous experiences, Extra high means that organization is completely familiar with this application domain.
Process maturity | Reflects the process maturity of the organization. Thus it is dependent on SEI-CMM level of the organization. | Very low means organization has no level at all and extra high means organization is related as highest level of SEI-CMM.

## Slide 87: Software Project Planning
Scaling factors | Very low | Low | Nominal | High | Very high | Extra high
Precedent ness | 6.20 | 4.96 | 3.72 | 2.48 | 1.24 | 0.00
Development flexibility | 5.07 | 4.05 | 3.04 | 2.03 | 1.01 | 0.00
Architecture/ Risk resolution | 7.07 | 5.65 | 4.24 | 2.83 | 1.41 | 0.00
Team cohesion | 5.48 | 4.38 | 3.29 | 2.19 | 1.10 | 0.00
Process maturity | 7.80 | 6.24 | 4.68 | 3.12 | 1.56 | 0.00
Table 13: Data for the Computation of B
The value of B can be calculated as:
B=0.91 + 0.01 * (Sum of rating on scaling factors for the project)

## Slide 88: Software Project Planning
Early design cost drivers
There are seven early design cost drivers and are given below:
Product Reliability and Complexity (RCPX)
Required Reuse (RUSE)
Platform Difficulty (PDIF)
Personnel Capability (PERS)
Personnel Experience (PREX)
Facilities (FCIL)
Schedule (SCED)

## Slide 89: Software Project Planning
Post architecture cost drivers
There are 17 cost drivers in the Post Architecture model. These are rated on a scale of 1 to 6 as given below :
The list of seventeen cost drivers is given below :
Reliability Required (RELY)
Database Size (DATA)
Product Complexity (CPLX)
Required Reusability (RUSE)

## Slide 90: Software Project Planning
Documentation (DOCU)
Execution Time Constraint (TIME)
Main Storage Constraint (STOR) viii.Platform Volatility (PVOL)
Analyst Capability (ACAP)
Programmers Capability (PCAP)
Personnel Continuity (PCON)
Analyst Experience (AEXP)

## Slide 91: Software Project Planning
Programmer Experience (PEXP)
Language & Tool Experience (LTEX)
Use of Software Tools (TOOL)
Site Locations & Communication Technology between Sites (SITE)
Schedule (SCED)

## Slide 92: Software Project Planning
Mapping of early design cost drivers and post architecture cost drivers
The 17 Post Architecture Cost Drivers are mapped to 7 Early Design Cost Drivers and are given in Table 14
Early Design Cost Drivers | Counter part Combined Post Architecture Cost drivers
RCPX | RELY, DATA, CPLX, DOCU
RUSE | RUSE
PDIF | TIME, STOR, PVOL
PERS | ACAP, PCAP, PCON
PREX | AEXP, PEXP, LTEX
FCIL | TOOL, SITE
SCED | SCED
Table 14: Mapping table

## Slide 93: Software Project Planning
Product of cost drivers for early design model
i. Product Reliability and Complexity (RCPX): The cost driver combines four Post Architecture cost drivers which are RELY, DATA, CPLX and DOCU.

## Slide 94
ii. Required Reuse (RUSE) : This early design model cost driver is same as its Post architecture Counterpart. The RUSE rating levels are (as per Table 16):
Software Project Planning

## Slide 95
iii. Platform Difficulty (PDIF) : This cost driver combines TIME, STOR and PVOL of Post Architecture Cost Drivers.
Software Project Planning

## Slide 96
iv. Personnel Capability (PERS) : This cost driver combines three Post Architecture Cost Drivers. These drivers are ACAP, PCAP and PCON.
Software Project Planning

## Slide 97
v. Personnel Experience (PREX) : This early design driver combines three Post Architecture Cost Drivers, which are AEXP, PEXP and LTEX.
Software Project Planning

## Slide 98
vi. Facilities (FCIL): This depends on two Post Architecture Cost Drivers, which are TOOL and SITE.
Software Project Planning

## Slide 99
vii.Schedule (SCED) : This early design cost driver is the same as Post Architecture Counterpart and rating level are given below using table 16.
Software Project Planning
100

## Slide 100: Software Project Planning
The seven early design cost drivers have been converted into numeric values with a Nominal value 1.0. These values are used for the calculation of a factor called “Effort multiplier” which is the product of all seven early design cost drivers. The numeric values are given in Table 15.
Table 15: Early design parameters
101

## Slide 101: Software Project Planning
The early design model adjusts the nominal effort using 7 effort multipliers (EMs). Each effort multiplier (also called drivers) has 7 possible weights as given in Table 15. These factors are used for the calculation of adjusted effort as given below:
PMadjusted effort may very even up to 400% from PMnominal
Hence PMadjusted is the fine tuned value of effort in the early design phase
 
7
 i7 
PMadjusted  PM nominal   EMi 
102

## Slide 102: Software Project Planning
Example: 4.10
A software project of application generator category with estimated 50 KLOC has to be developed. The scale factor (B) has low precedentness, high development flexibility and low team cohesion. Other factors are nominal. The early design cost drivers like platform difficult (PDIF) and Personnel Capability (PERS) are high and others are nominal. Calculate the effort in person months for the development of the project.
103

## Slide 103: Software Project Planning
Solution
Here
B = 0.91 + 0.01 * (Sum of rating on scaling factors for the project)
= 0.91 + 0.01 * (4.96 + 2.03 + 4.24 + 4.38 + 4.68)
= 0.91 + 0.01(20.29)=1.1129
PMnominal = A*(size)B
= 2.5 * (50)1.1129 = 194.41 Person months
The 7 cost drivers are
PDIF = high (1.29) PERS = high (0.83)
RCPX = nominal (1.0) RUSE = nominal (1.0) PREX = nominal (1.0) FCIL = nominal (1.0) SCEO = nominal (1.0)
104

## Slide 104: Software Project Planning
= 194.41 * [1.29 x 0.83)
= 194.41 x 1.07
= 208.155 Person months
105

## Slide 105: Software Project Planning
Post Architecture Model
The post architecture model is the most detailed estimation model and is intended to be used when a software life cycle architecture has been completed. This model is used in the development and maintenance of software products in the application generators, system integration or infrastructure sectors.

 17
 i7 
PMadjusted  PM nominal   EMi 
EM : Effort multiplier which is the product of 17 cost drivers.
The 17 cost drivers of the Post Architecture model are described in the table 16.
106

## Slide 106: Software Project Planning
Cont…
Table 16: Post Architecture Cost Driver rating level summary
107

## Slide 107: Software Project Planning
Table 16: Post Architecture Cost Driver rating level summary
Cont…
108

## Slide 108: Software Project Planning
Table 16: Post Architecture Cost Driver rating level summary
Cont…
109

## Slide 109: Software Project Planning
Table 16: Post Architecture Cost Driver rating level summary
110

## Slide 110: Software Project Planning
Product complexity is based on control operations, computational operations, device dependent operations, data management operations and user interface management operations. Module complexity rating are given in table 17.
The numeric values of these 17 cost drivers are given in table 18 for the calculation of the product of efforts i.e., effort multiplier (EM). Hence PM adjusted is calculated which will be a better and fine tuned value of effort in person months.
111

## Slide 111: Software Project Planning
 | Control Operations | Computational Operations | Device- dependent Operations | Data management Operations | User Interface Management Operations
Very | Straight-line code | Evaluation of | Simple read, | Simple arrays in | Simple input
Low | with a few non- | simple | write statements | main memory. | forms, report
 | nested structured | expressions: e.g., | with simple | Simple COTSDB | generators.
 | programming | A=B+C*(D-E) | formats. | queries, updates. | 
 | operators: Dos. |  |  |  | 
 | Simple module |  |  |  | 
 | composition via |  |  |  | 
 | procedure calls or |  |  |  | 
 | simple scripts. |  |  |  | 
Low | Straight forward | Evaluation of | No cognizance | Single file sub | User of simple
 | nesting of | moderate-level | needed of | setting with no data | graphics user
 | structured | expressions: e.g., | particular | structure changes, | interface (GUI)
 | programming | D=SQRT(B**2- | processor or I/O | no edits, no | builders.
 | operators. Mostly | 4*A*C) | device | intermediate files, | 
 | simple predicates |  | characteristics. | Moderately | 
 |  |  | I/O done at | complex COTS-DB | 
 |  |  | GET/PUT level. | queries, updates. | 
Table 17: Module complexity ratings
Software Engineering (3rd ed.), By K.K Aggarwal & Yogesh Singh, Copyright © New Age International Publishers, 2007
Cont…
112

## Slide 112: Software Project Planning
 | Control Operations | Computational Operations | Device- dependent Operations | Data management Operations | User Interface Management Operations
Nominal | Mostly simple nesting. | Use of standard | I/O processing | Multi-file input | Simple use of
 | Some inter module | maths and | includes | and single file | widget set.
 | control Decision tables. | statistical | device | output. Simple | 
 | Simple callbacks or | routines. Basic | selection, | structural | 
 | message passing, | matrix/ vector | status | changes, simple | 
 | including middleware | operations. | checking and | edits. Complex | 
 | supported distributed |  | error | COTS-DB | 
 | processing. |  | processing. | queries, | 
 |  |  |  | updates. | 
High | Highly nested | Basic numerical | Operations at | Simple triggers | Widget set
 | structured | analysis: | physical I/O | activated by data | development
 | programming operators | multivariate | level (physical | stream contents. | and
 | with many compound | interpolation, | storage | Complex data | extension.
 | predicates. Queue and | ordinary | address | restructuring. | Simple voice
 | stack control. | differential | translations; |  | I/O
 | Homogeneous, | equations. Basic | seeks, read |  | multimedia.
 | distributed processing. | truncation, round | etc.) |  | 
 | Single processor soft | off concerns. | Optimized I/O |  | 
 | real time control. |  | overlap. |  | 
Table 17: Module complexity ratings
Software Engineering (3rd ed.), By K.K Aggarwal & Yogesh Singh, Copyright © New Age International Publishers, 2007
Cont…
113

## Slide 113: Software Project Planning
 | Control Operations | Computational Operations | Device-dependent Operations | Data management Operations | User Interface Management Operations
Very | Reentrant and | Difficult but | Routines for | Distributed | Moderately
High | recursive coding. | structured | interrupt | database | complex
 | Fixed-priority | numerical analysis: | diagnosis, | coordination. | 2D/3D,
 | interrupt handling. | near singular | servicing, | Complex | dynamic
 | Task | matrix equations, | masking. | triggers. Search | graphics,
 | synchronization, | partial differential | Communication | optimization. | multimedia.
 | complex callbacks, | equations. Simple | line handling. |  | 
 | heterogeneous | parallelization. | Performance |  | 
 | distributed |  | intensive |  | 
 | processing. Single |  | embedded |  | 
 | processor hard real |  | systems. |  | 
 | time control. |  |  |  | 
Extra | Multiple resource | Difficult and | Device timing | Highly coupled, | Complex
High | scheduling with | unstructured | dependent coding, | dynamic | multimedia,
 | dynamically | numerical analysis: | micro | relational and | virtual reality.
 | changing priorities. | highly accurate | programmed | object | 
 | Microcode-level | analysis of noisy, | operations. | structures. | 
 | control. Distributed | stochastic data. | Performance | Natural | 
 | hard real time | Complex | critical embedded | language data | 
 | control. | parallelization. | systems. | management. | 
Table 17: Module complexity ratings
Software Engineering (3rd ed.), By K.K Aggarwal & Yogesh Singh, Copyright © New Age International Publishers, 2007
114

## Slide 114: Software Project Planning
Table 18: 17 Cost Drivers
Cost Driver | Rating |  |  |  |  | 
 | Very Low | Low | Nominal | High | Very High | Extra High
RELY | 0.75 | 0.88 | 1.00 | 1.15 | 1.39 | 
DATA |  | 0.93 | 1.00 | 1.09 | 1.19 | 
CPLX | 0.75 | 0.88 | 1.00 | 1.15 | 1.30 | 1.66
RUSE |  | 0.91 | 1.00 | 1.14 | 1.29 | 1.49
DOCU | 0.89 | 0.95 | 1.00 | 1.06 | 1.13 | 
TIME |  |  | 1.00 | 1.11 | 1.31 | 1.67
STOR |  |  | 1.00 | 1.06 | 1.21 | 1.57
PVOL |  | 0.87 | 1.00 | 1.15 | 1.30 | 
ACAP | 1.50 | 1.22 | 1.00 | 0.83 | 0.67 | 
PCAP | 1.37 | 1.16 | 1.00 | 0.87 | 0.74 | 
Cont…
115

## Slide 115: Software Project Planning
Table 18: 17 Cost Drivers
Cost Driver | Rating |  |  |  |  | 
 | Very Low | Low | Nominal | High | Very High | Extra High
PCON | 1.24 | 1.10 | 1.00 | 0.92 | 0.84 | 
AEXP | 1.22 | 1.10 | 1.00 | 0.89 | 0.81 | 
PEXP | 1.25 | 1.12 | 1.00 | 0.88 | 0.81 | 
LTEX | 1.22 | 1.10 | 1.00 | 0.91 | 0.84 | 
TOOL | 1.24 | 1.12 | 1.00 | 0.86 | 0.72 | 
SITE | 1.25 | 1.10 | 1.00 | 0.92 | 0.84 | 0.78
SCED | 1.29 | 1.10 | 1.00 | 1.00 | 1.00 | 
116

## Slide 116: Software Project Planning
Schedule estimation
Development time can be calculated using PMadjusted as a key factor and the desired equation is:
100
TDEV
nominal adjusted
SCED%
)(0.280.2( B0.091))]
 [  (PM
where Φ = constant, provisionally set to 3.67
TDEVnominal = calendar time in months with a scheduled constraint B = Scaling factor
PMadjusted = Estimated effort in Person months (after adjustment)
117

## Slide 117: Software Project Planning
be calibrated
Size measurement
Size can be measured in any unit and the model can accordingly. However, COCOMO II details are:
Application composition model uses the size in object points.
The other two models use size in KLOC
Early design model uses unadjusted function points. These function points are converted into KLOC using Table 19. Post architecture model may compute KLOC after defining LOC counting rules. If function points are used, then use unadjusted function points and convert it into KLOC using Table 19.
118

## Slide 118: Software Project Planning
Software Engineering (3rd ed.), By K.K Aggarwal & Yogesh Singh, Copyright © New Age International Publishers, 2007
Language | SLOC/UFP
Ada | 71
AI Shell | 49
APL | 32
Assembly | 320
Assembly (Macro) | 213
ANSI/Quick/Turbo Basic | 64
Basic-Compiled | 91
Basic-Interpreted | 128
C | 128
C++ | 29
Table 19: Converting function points to lines of code
Cont…119

## Slide 119: Software Project Planning
Language | SLOC/UFP
ANSI Cobol 85 | 91
Fortan 77 | 105
Forth | 64
Jovial | 105
Lisp | 64
Modula 2 | 80
Pascal | 91
Prolog | 64
Report Generator | 80
Spreadsheet | 6
Table 19: Converting function points to lines of code
120

## Slide 120: Software Project Planning
Example: 4.11
Consider the software project given in example 4.10. Size and scale factor
(B) are the same. The identified 17 Cost drivers are high reliability (RELY), very high database size (DATA), high execution time constraint (TIME), very high analyst capability (ACAP), high programmers capability (PCAP). The other cost drivers are nominal. Calculate the effort in Person-Months for the development of the project.
121

## Slide 121: Software Project Planning
Solution
Here
PMnominal
B = 1.1129
= 194.41 Person-months
= 194.41 x (1.15 x 1.19 x 1.11 x 0.67 x 0.87)
= 194.41 x 0.885
= 172.05 Person-months

 17
 i7 
 PM nominal   EMi 
PMadjusted
122

## Slide 122: Software Project Planning
Time
Fig.6: The Rayleigh manpower loading curve
Putnam Resource Allocation Model
Norden of IBM
Rayleigh curve
Model for a range of hardware development projects.
Overall Curve Design and Coding
Persons
123

## Slide 123: Software Project Planning
Putnam observed that | this | curve was | a close
approximation at project | level | and software | subsystem
level. |  |  | 
No. of projects = 150
124

## Slide 124: Software Project Planning
dt = manpower utilization rate per unit time
a = parameter that affects the shape of the curve K = area under curve in the interval [0, ∞ ]
t = elapsed time
dy
dt
m(t)  dy  2kateat 2
--------- (1)
The Norden / Rayleigh Curve
The curve is modeled by differential equation
125

## Slide 125: Software Project Planning
On Integration on interval [o, t]
y(t) = K [1-e-at2] -------------(2)
Where y(t): cumulative manpower used upto time t.
y(0) = 0
y(∞) = k
The cumulative manpower is null at the start of the project, and grows monotonically towards the total effort K (area under the curve).
126

## Slide 126: Software Project Planning
2
2
2
[1 2at ]  0
 2kae
dt 2
d y
at
d
2a
t 2
 1
“td”: time where maximum effort rate occurs Replace “td” for t in equation (2)
1
d
2 t
t 2
2t 2
d
d
2
a 
E  y (t )  0.3935 k







E  y (t )  k 1  e
  K (1  e  0.5 )
127

## Slide 127: Software Project Planning
Replace “a” with
in the Norden/Rayleigh model. By
1
d
making this substitution in equation we have
2t 2
d
2t 2
t 2
d
te
2t 2
2K

m(t) 
2
d
2t
t 2
d
te
t 2
K


128

## Slide 128: Software Project Planning
m (t) Person
a=2
a=0.5
a=0.222
a=0.125
Time (years)
Fig.7: Influence of parameter ‘a’ on the manpower
distribution
129

## Slide 129: Software Project Planning
At time t=td, peak manning m (td) is obtained and denoted by mo.
k
td e
o
m 
k td m0 e
= Total project cost/effort in person-years.
= Delivery time in years
= No. of persons employed at the peak
= 2.71828
130

## Slide 130: Software Project Planning
Example: 4.12
A software development project is planned to cost 95 MY in a period of 1 year and 9 months. Calculate the peak manning and average rate of software team build up.
131

## Slide 131: Software Project Planning
95
 32.94  33 persons
1.751.648
Average rate of software team build up
td 1.75
33
 18.8 persons / year or 1.56 person / month
m0
 
Peak manning
mo=
t e
k=95 MY
td = 1.75 years
k
d
Solution
Software development cost Peak development time
132

## Slide 132: Software Project Planning
Example: 4.13
Consider a large-scale project for which the manpower requirement is K=600 PY and the development time is 3 years 6 months.
Calculate the peak manning and peak time.
What is the manpower cost after 1 year and 2 months?
133

## Slide 133: Software Project Planning
NOW
 m0 
Solution
(a) We know td=3 years and 6 months = 3.5 years
600/(3.5x1.648)  104 persons
m
 K td e
0
134

## Slide 134: y(t)  K 1 eat 2 
(b) We know
t = 1 year and 2 months
= 1.17 years
1 1
2  (3.5)2
  0.041
d
2t 2
a 
y (1.17 )  600 1  e  0.041 (1.17 ) 2 
= 32.6 PY
Software Project Planning
135

## Slide 135: Software Project Planning
2
2
2
dt 2
d y
(1 2at )
m'(t)   2kae
at
Then, for t=0
d
d
t 2
2t 2
m'(0)  2Ka  2K  K
Difficulty Metric
Slope of manpower distribution curve at start time t=0 has some useful properties.
136

## Slide 136: Software Project Planning
The ratio is called difficulty and denoted by D,
which is measured in person/year :
d
t 2
K
D=
persons/year
d
t2
k
137

## Slide 137: Software Project Planning
Project is difficult to develop if
Manpower demand is high
When time schedule is short
138

## Slide 138: Software Project Planning
Peak manning is defined as:
Thus difficult projects tend to have a higher peak manning for a given development time, which is in line with Norden’s observations relative to the parameter “a”.
k
td e
m 
0
d d
t
e
t 2
D  k  m0
139

## Slide 139: Software Project Planning
t 3
d
d
D'(t )  2k persons / year 2
t 2
D'(k)  1 year 2
d
Manpower buildup
D is dependent upon “K”. The derivative of D relative to “K” and “td” are
140

## Slide 140: Software Project Planning
D1(K) will always be very much smaller than the absolute value of D1(td). This difference in sensitivity is shown by considering two projects
Project A Project B
: Cost = 20 PY & td = 1 year
: Cost = 120 PY & td = 2.5 years
Project A Project B
: D` (td) = -40 & D`(K) = 1
: D` (td) = -15.36 & D`(K) = 0.16
The derivative values are
This shows that a given software development is time sensitive.
141

## Slide 141: Software Project Planning
Putnam observed that
Difficulty derivative relative to time
Behavior of s/w development
If project scale is increased, the development time also
increase to such an extent that
remains constant
d
around a value which could be 8,15,27.
t 3
k
142

## Slide 142: Software Project Planning
It is represented by D0 and can be expressed as:
0
t 3
d
D  k person / year 2
D0 =8, new s/w with many interfaces & interactions with other systems.
D0 =15, New standalone system.
D0 =27, The software is rebuild form existing software.
143

## Slide 143: Software Project Planning
Example: 4.14
Consider the example 4.13 and calculate the difficulty and manpower build up.
144

## Slide 144: Software Project Planning
Solution
We know
d
t 2
D  K
Difficulty
600
(3.5)2
 49 person / year

Manpower build up can be calculated by following equation
0
d
t 3
D  K
(3.5)3
600
 14 person / year 2

145

## Slide 145: Software Project Planning
P =
cumulative manpower used to produce code
Productivity Versus Difficulty
Productivity = No. of LOC developed per person-month
P ∞ Dβ
Avg. productivity
LOC produced
146

## Slide 146: Software Project Planning
2
k (0.3935)
t
 2
3
 
 d 
 k 
S  
S  0.3935 K 1/ 3td
4 / 3
P = S/E
P  D2 / 3
S  D2 / 3 E
 D2 / 3 (0.3935 K )
147

## Slide 147: Software Project Planning
c
Technology Factor
Programming environment
Hardware constraints
Complexity
Experience
0.39
148

## Slide 148: Software Project Planning
C
610 – 57314
K : P-Y
T : Years
1/ 3 4 / 3
td
S  CK
1/ 3 4 / 3
td
C  S.K
3
4





C
1  S
K 
t d
The trade off of time versus cost
K 1/ 3t 4 / 3  S / C
d
149

## Slide 149: Software Project Planning
C = 5000
S = 5,00,000 LOC
d
t 4
K  1 (100 )3
td (years) | K (P-Y)
5.0 | 1600
4.0 | 3906
3.5 | 6664
3.0 | 12346
Table 20: (Manpower versus development time)
150

## Slide 150: Software Project Planning
Development Subcycle
All that has been discussed so far is related to project life cycle as represented by project curve
Manpower
distribution
Fig.8: Project life cycle
Maintenance
Project
Test & Validation
Design code development
Requirements & Specification
Time
151

## Slide 151: Software Project Planning
Development Curve
Test & Validation Curve
Project life cycle
Project curve is the addition of two curves
152

## Slide 152: Software Project Planning
 md (t) = 2kdbt e-bt2 yd (t) = Kd [1-e-bt2]
An examination of md(t) function shows a non-zero value of md at time td.
This is because the manpower involved in design & coding is still completing this activity after td in form of rework due to the validation of the product.
Nevertheless, for the model, a level of completion has to be assumed for development.
It is assumed that 95% of the development will be completed by the time td.
153

## Slide 153: Software Project Planning
bt2
 1 e  0.95
Kd
yd (t)
1
od
2t 2
b 
Tod: time at which development curve exhibits a peak manning.
6
od
t d
t 
We may say that
154

## Slide 154: Software Project Planning
Relationship between Kd & K must be established.
At the time of origin, both cycles have the same slope.
d
dt
tod
 
 o
 
 K  Kd 
 
 dt o td
 dm  dm
2
2
Kd=K/6
od
d
t 2 t 2
 K d
D  K
155

## Slide 155: Software Project Planning
This does not apply to the manpower build up D0.
Conte investigated that Larger projects
Medium & small projects
reasonable overestimate
od
d
o
6t 3
Kd
t 3
D  K 
156

## Slide 156: Software Project Planning
Example: 4.15
A software development requires 90 PY during the total development sub-cycle. The development time is planned for a duration of 3 years and 5 months
Calculate the manpower cost expended until development time
Determine the development peak time
Calculate the difficulty and manpower build up.
157

## Slide 157: Software Project Planning
Solution
(a) Duration td = 3.41 years
Kd
yd (td )  0.95
Yd (td )  0.95 90
= 85.5 PY
We know from equation
 0.95
Kd
yd (t)  1 e btd
158

## Slide 158: Software Project Planning
(b) We know from equation
6
t d
tod

t d
od
6
 3 .41 / 2 .449  1 .39 years
t 
 17 months
159

## Slide 159: Software Project Planning
d
(c) Total Manpower development
Kd  yd (td ) / 0.95
= 85.5 / 0.95 = 90
K  6Kd  90 6  540PY
D  K / t 2  540 /(3.41)2  46 persons/years
d
o
t 3
D  K  540 /(3.41)3  13.6
persons/years2
160

## Slide 160: Software Project Planning
Example:4.16
A software development for avionics has consumed 32 PY up to development cycle and produced a size of 48000 LOC. The development of project was completed in 25 months. Calculate the development time, total manpower requirement, development peak time, difficulty, manpower build up and technology factor.
161

## Slide 161: Software Project Planning
d
0.95 0.95
k  Yd (td )  32  33.7 PY
od
6
t  (td )  0.85 years  10 months
K = 6Kd = 6 x 33.7 = 202 PY
d
202
(2.08)2
t 2
 46.7 pesons / years
D  k 
Solution:
Development time td = 25 months = 2.08 years
Total manpower development
Development peak time
162

## Slide 162: Software Project Planning
0
202
t 3
d
(2.08)3
 22.5 Persons / year 2
D  k 
Technology factor
C  SK 1/ 3t 4 / 3
d
= 3077
163

## Slide 163: Software Project Planning
Example 4.17
What amount of software can be delivered in 1 year 10 months in an organization whose technology factor is 2400 if a total of 25 PY is permitted for development effort.
164

## Slide 164: Software Project Planning
Solution:
1 / 3 t 4 / 3
d
= 2400 x 5.313 x 2.18 = 27920 LOC
We know
td = 1.8 years Kd = 25 PY
K = 25 x 6 = 150 PY
C = 2400
S  CK
165

## Slide 165: Software Project Planning
Example 4.18
The software development organization developing real time software has been assessed at technology factor of 2200. The maximum value of manpower build up for this type of software is Do=7.5. The estimated size to be developed is S=55000 LOC.
(a) Determine the total development development manpower cost, the
time, difficulty
the total and the
development peak manning.
(b) The development time determined in (a) is considered too long. It is recommended that it be reduced by two months. What would happen?
166

## Slide 166: Software Project Planning
Solution
S  CK 1/ 3t 4 / 3
d
3
d
 kt 4
 
 c 
 s 
3
o d
 D t 7
 
 C 
 S 
  
1/ 7
 1  S 3 
 D0  C  
td  
We have
which is also equivalent to
then
167

## Slide 167: Software Project Planning
C
Since S  25
td = 3 years
06
202
33.75PY
D = D0td = 22.5 persons / year
t
od
6 6
  1.2 years
 td 3
Total development manpower cost Kd 
0 d
K  D t3  7.5 27  202 PY
168

## Slide 168: Software Project Planning
Here
2
Md(t) = 2kd bte-bt
2
Yd(t) = kd (1-e-bt )
t = tod
e1/ 2
od
= 22.5 x 1.2 x .606
= 16 persons
Peak manning  mod  Dt
169

## Slide 169: Software Project Planning
III. If development time is reduced by 2 months
Developing s/w at higher manpower build-up
Producing less software
170

## Slide 170: Software Project Planning
7  
 C 
 1  S 
D
td
o
Now td = 3 years – 2 months = 2.8 years
Do  (25)3 /(2.8)7  11.6 persons / years
0 d
k  D t3  254 PY
(i) Increase Manpower Build-up
3
d
6
K  254  42.4 PY
171

## Slide 171: Software Project Planning
D = D0td = 32.5 persons / year
The peak time is Peak manning
tod = 1.14 years mod = Dtod e-0.5
= 32.5 x 1.14 x 0.6
= 22 persons
Note the huge increase in peak manning & manpower cost.
172

## Slide 172: Software Project Planning
3
 
0 d
 D t 7  7.5 (2.8)7  10119.696
 C 
 S 
3
 21.62989
 
 C 
 S 
Then for
C=2200 S=47586 LOC
(ii) Produce Less Software
173

## Slide 173: Productivity versus difficult
Example 4.19
A stand alone project for which the size is estimated at 12500 LOC is to be developed in an environment such that the technology factor is 1200. Choosing a manpower build up Do=15, Calculate the minimum development time, total development man power cost, the difficulty, the peak manning, the development peak time, and the development productivity.
174

## Slide 174: Software Project Planning
d
S  CK 1/ 3t 4 / 3
= 12500 LOC
= 1200
= 15
Solution
Size (S)
Technology factor (C) Manpower buildup (Do)
Now
d
C
S  K1/ 3t 4 / 3
3
d
 Kt 4
 
 C 
 S 
175

## Slide 175: Software Project Planning
d
o
t 3
Also we know D
 K
7
3
o d
S
 Dt

 
C

15

 
(10.416)3 1/ 7
td  
Substituting the values, we get
K  D t3  D t3
o d o d
Hence
3
d
 15t 7
 
 1200 
 12500 
td  1.85 years
176

## Slide 176: Software Project Planning
(i) Hence Minimum development time (td)=1.85 years
(ii) Total development manpower cost
6
K
d
 K
d
d
6 6
K  K  94.97  15.83 PY
=15(1.85)3=94.97 PY
Hence K 15t3
(iii) Difficulty
d
94.97
(1.85)2
t 2
 27.75 Persons / year
D  K 
177

## Slide 177: Software Project Planning
(iv) Peak Manning
K
td e
m 
0
94.97
31.15Person
1.851.648

(v) Development Peak time
6
od
t
 td
2.449
 0.755 years
 1.85
178

## Slide 178: Software Project Planning
(vi) Development Productivity
No .of lines of code ( S )
effort ( K d )

15.83
 12500  789.6 LOC / PY
179

## Slide 179: Software Project Planning
Software Risk Management
We Software developers are extremely optimists.
We assume, everything will go exactly as planned.
Other view
not possible to predict what is going to happen ?
Software surprises Never good news
180

## Slide 180: Software Project Planning
management is required to reduce this surprise
Risk factor
Dealing with concern before it becomes a crisis.
Quantify probability of failure & consequences of failure.
181

## Slide 181: Software Project Planning
What is risk ?
Tomorrow’s problems are today’s risks.
“Risk is a problem that may cause some loss or threaten the success of the project, but which has not happened yet”.
182

## Slide 182: Software Project Planning
Risk management is the process of identifying addressing and eliminating these problems before they can damage the project.
Current problems &
Potential Problems
183

## Slide 183: Software Project Planning
Typical Software Risk
Capers Jones has identified the top five risk factors that threaten projects in different applications.
Dependencies on outside agencies or factors.
  Availability of trained, experienced persons
  Inter group dependencies
  Customer-Furnished items or information
  Internal & external subcontractor relationships
184

## Slide 184: Software Project Planning
2.
Requirement issues
Uncertain requirements
surprises and
Wrong product
or
Right product badly
Either situation results in unpleasant unhappy customers.
185

## Slide 185: Software Project Planning
Lack of clear product vision
Lack of agreement on product requirements
Unprioritized requirements
New market with uncertain needs
Rapidly changing requirements
Inadequate Impact analysis of requirements changes
186

## Slide 186: Software Project Planning
3. Management Issues
Project managers plans, and most
usually write the risk management people do not wish to air their
weaknesses in public.
Inadequate planning
Inadequate visibility into actual project status
Unclear project ownership and decision making
Staff personality conflicts
Unrealistic expectation
Poor communication
187

## Slide 187: Software Project Planning
4.
Lack of knowledge
Inadequate training
Poor understanding of methods, tools, and techniques
Inadequate application domain experience
documented or neglected
New Technologies
Ineffective, poorly processes
188

## Slide 188: Software Project Planning
5.
Other risk categories
Unavailability of adequate testing facilities
Turnover of essential personnel
Unachievable performance requirements
Technical approaches that may not work
189

## Slide 189: Software Project Planning
Risk Management
Risk Assessment
Risk Control
Risk Identification
Risk Analysis
Risk Prioritization
Risk Management Planning
Risk Monitoring
Risk Resolution
Risk Management Activities
Fig. 9: Risk Management Activities
190

## Slide 190: Software Project Planning
Risk Assessment
Identification of risks
Risk analysis involves examining how project outcomes might change with modification of risk input variables.
Risk prioritization focus for severe risks.
Risk exposure: It is the product of the probability of incurring a loss due to the risk and the potential magnitude of that loss.
191

## Slide 191: Software Project Planning
Another way of handling risk is the risk avoidance. Do not do the risky things! We may avoid risks by not undertaking certain projects, or by relying on proven rather than cutting edge technologies.
192

## Slide 192: Software Project Planning
Risk Control
Risk Management Planning produces a plan for dealing with each significant risks.
Record decision in the plan.
Risk resolution is the execution of the plans of dealing with each risk.
193

## Slide 193: Multiple Choice Questions
(a) Size
(c) Development time
(b) Cost
(d) All of the above.
4.2 Which one is not a size measure for software
(a) LOC
(c) Cyclomatic Complexity
(b) Function Count
(d) Halstead’s program length
4.3 Function count method was developed by
(a) B.Beizer
(c) M.halstead
(b) B.Boehm
(d) Alan Albrecht
4.4 Function point analysis (FPA) method decomposes the system into functional units. The total number of functional units are
(a) 2
(c) 4
(b) 5
(d) 1
Note: Choose most appropriate answer of the following questions:
4.1 After the finalization of SRS, we may like to estimate
194

## Slide 194: Multiple Choice Questions
(a) UFP * CAF
(c) UFP * Cost
(b) UFP * FAC
(d) UFP * Productivity
  IFPUG stand for
    Initial function point uniform group
    International function point uniform group
    International function point user group
    Initial function point user group
  Function point can be calculated by
195
  Putnam resource allocation model is based on
    Function points
    Norden/ Rayleigh curve
    Putnam theory of software management
    Boehm’s observation on manpower utilisation rate
  Manpower buildup for Putnam resource allocation model is
    K / t 2 persons / year 2 (b) K / t 3 persons / year 2
d d
(c) K / t 2 persons / year (d ) K / t 3 persons / year
d d

## Slide 195: Multiple Choice Questions
(b) Gregg Rothermal
(d) Rajiv Gupta
  COCOMO was developed initially by
    B.W.Bohem
(c) B.Beizer
  A COCOMO model is
    Common Cost estimation model
    Constructive cost Estimation model
    Complete cost estimation model
196
(d) Comprehensive Cost estimation model
4.11 Estimation of software development effort for organic software is COCOMO is
(a) E=2.4(KLOC)1.05PM
(c) E=2.0(KLOC)1.05PM
(b) E=3.4(KLOC)1.06PM
(d) E-2.4(KLOC)1.07PM
4.12 Estimation of size for a project is dependent on
(a) Cost
(c) Time
(b) Schedule
(d) None of the above
4.13 In function point analysis, number of Complexity adjustment factor are
(a) 10
(c) 14
(b) 20
(d) 12

## Slide 196: Multiple Choice Questions
4.14 COCOMO-II estimation model is based on
(a) Complex approach
(c) Bottom up approach
(b) Algorithm approach
(d) Top down approach
4.15 Cost estimation for a project may include
(a) Software Cost
(c) Personnel Costs
(b) Hardware Cost
(d) All of the above
4.16 In COCOMO model, if project size is typically 2-50 KLOC, then which mode is to be selected?
(b) Semidetached
(d) None of the above
(a) Organic
(c) Embedded
  COCOMO-II was developed at
    University of Maryland
(c) IBM
197
(b) University of Southern California
(d) AT & T Bell labs
4.18 Which one is not a Category of COCOMO-II
(a) End User Programming
(c) Requirement Sector
(b) Infrastructure Sector
(d) System Integration

## Slide 197: Multiple Choice Questions
4.19 Which one is not an infrastructure software?
198
(a) Operating system
(c) Compilers
(b) Database management system
(d) Result management system
  How many stages are in COCOMO-II?
    2
(c) 4
(b) 3
(d) 5
  Which one is not a stage of COCOMO-II?
    Application Composition estimation model
    Early design estimation model
    Post architecture estimation model
    Comprehensive cost estimation model
  In Putnam resource allocation model, Rayleigh curve is modeled by the equation
2
(a) m(t)  2at eat
2
(c) m(t)  2Kat eat
2
(b) m(t)  2Kt eat
2
(d ) m(t)  2Kbt eat

## Slide 198: Multiple Choice Questions
4.23 In Putnam resource allocation model, technology factor ‘C’ is defined as
  Risk management activities are divided in
    3 Categories
(c) 5 Categories
(b) 2 Categories
(d) 10 Categories
4.25 Which one is not a risk management activity?
199
(a) Risk assessment
(c) Risk generation
(b) Risk control
(d) None of the above
d
(a) C  SK 1/ 3t 4 / 3
d
(b) C  SK1/ 3t 4 / 3
d
(c) C  SK 1/ 3t 4 / 3
d
(d ) C  SK 1/ 3t 4 / 3

## Slide 199: Exercises
  What are various activities during software project planning?
  Describe any two software size estimation techniques.
  A proposal is made to count the size of ‘C’ programs by number of semicolons, except those occurring with literal strings. Discuss the strengths and weaknesses to this size measure when compared with the lines of code count.
  Design a LOC counter for counting LOC automatically. Is it language dependent? What are the limitations of such a counter?
  Compute the function point value for a project with the following information domain characteristics.
Number of user inputs = 30 Number of user outputs = 42 Number of user enquiries = 08 Number of files = 07
Number of external interfaces = 6
Assume that all complexity adjustment values are moderate.
200

## Slide 200: Exercises
Why FPs are becoming
201
4.6 Explain the concept of function points. acceptable in industry?
  What are the size metrics? How is function point metric advantageous over LOC metric? Explain.
  Is it possible to estimate software size before coding? Justify your answer with suitable example.
  Describe the Albrecht’s function count method with a suitable example.
  Compute the function point FP for a payroll program that reads a file of employee and a file of information for the current month and prints cheque for all the employees. The program is capable of handling an interactive command to print an individually requested cheque immediately.

## Slide 201: Exercises
  Assume that the previous payroll program is expected to read a file containing information about all the cheques that have been printed. The file is supposed to be printed and also used by the program next time it is run, to produce a report that compares payroll expenses of the current month with those of the previous month. Compute functions points for this program. Justify the difference between the function points of this program and previous one by considering how the complexity of the program is affected by adding the requirement of interfacing with another application (in this case, itself).
  Explain the Walson & Felix model and compare with the SEL model.
  The size of a software product to be developed has been estimated to be 22000 LOC. Predict the manpower cost (effort) by Walston-Felix Model and SEL model.
  A database system is to be developed. The effort has been estimated to be 100 Persons-Months. Calculate the number of lines of code and productivity in LOC/Person-Month.
202

## Slide 202: Exercises
  Discuss various types of COCOMO mode. Explain the phase wise distribution of effort.
  Explain all the levels of COCOMO model. Assume that the size of an organic software product has been estimated to be 32,000 lines of code. Determine the effort required to developed the software product and the nominal development time.
  Using the basic COCOMO model, under all three operating modes, determine the performance relation for the ratio of delivered source code lines per person-month of effort. Determine the reasonableness of this relation for several types of software projects.
  The effort distribution for a 240 KLOC organic mode software development project is: product design 12%, detailed design 24%, code and unit test 36%, integrate and test 28%. How would the following changes, from low to high, affect the phase distribution of effort and the total effort: analyst capability, use of modern programming languages, required reliability, requirements volatility?
203

## Slide 203: Exercises
  Specify, design, and develop a program that implements COCOMO. Using reference as a guide, extend the program so that it can be used as a planning tool.
  Suppose a system for office automation is to be designed. It is clear from requirements that there will be five modules of size 0.5 KLOC, 1.5 KLOC, 2.0 KLOC, 1.0 KLOC and 2.0 KLOC respectively. Complexity, and reliability requirements are high. Programmer’s capability and experience is low. All other factors are of nominal rating. Use COCOMO model to determine overall cost and schedule estimates. Also calculate the cost and schedule estimates for different phases.
  Suppose that a project was estimated to be 600 KLOC. Calculate the effort and development time for each of the three modes i.e., organic, semidetached and embedded.
  Explain the COCOMO-II in detail. What types of categories of projects are identified?
204

## Slide 204: Exercises
  Discuss the Infrastructure Sector of COCOMO-II.
  Describe various stages of COCOMO-II. Which stage is more popular and why?
  A software project of application generator category with estimated size of 100 KLOC has to be developed. The scale factor (B) has high percedentness, high development flexibility. Other factors are nominal. The cost drivers are high reliability, medium database size, high Personnel capability, high analyst capability. The other cost drivers are nominal. Calculate the effort in Person-Months for the development of the project.
  Explain the Putnam resource allocation model. What are the limitations of this model?
  Describe the trade-off between time versus cost in Putnam resource allocation model.
  Discuss the Putnam resources allocation model. Derive the time and effort equations.
205

## Slide 205: Exercises
  Assuming the Putnam model, with S=100,000 , C=5000, Do=15, Compute development time td and manpower development Kd.
  Obtain software productivity data for two or three software development programs. Use several cost estimating models discussed in this chapter. How to the results compare with actual project results?
  It seems odd that cost and size estimates are developed during software project planning-before detailed software requirements analysis or design has been conducted. Why do we think this is done? Are there circumstances when it should not be done?
  Discuss typical software risks. How staff turnover problem affects software projects?
  What are risk management activities? Is it possible to prioritize the risk?
206

## Slide 206: Exercises
  What is risk exposure? What techniques can be used to control each risk?
  What is risk? Is it economical to do risk management? What is the effect of this activity on the overall cost of the project?
  There are significant risks even in student projects. Analyze a student project and list all the risk.
207